## Live Projects
Lower Mersey Action Plan
Project Name & Brief Description | Key Drivers | 1. Developing an evidence base | 2. Delivering cleaner and healthier waterbodies | 3. Delivering Integrated Water Management | 4. Opportunities for using the water environment | 5. Engaging the community | Lead (name & org.) | Additional partners (name and org.) | Cost (£) | Target funding streams | Delivery date | Updates | RAG
Court Hey Park NFM/SuDS Pilot project highlghted through the NFM opportunity modelling. The project will look to provide off-line flood storage and at the same time look to mitigate diffuse pollution in Court Hey Brook. Linked to proposed Court Hey wetland project | Flood risk, water quality, public engagement, volunteering |  | ü | ü | ü | ü | Knowsley Council | Paul Corner, Mersey Rivers Trust United Utilities Andrea Robson, Environment Agency | £10k initial funding. £30k capital | FDGiA, Local Levy | 2021-03-31 | July 2020: Delivery planned for 2020-21 | Developing
Court Hey Park Wetland Creation Create a wetland in Court Hey Park with improved footpaths for access. | Access and recreation, water quality, public engagement, volunteering |  | ü | ü | ü | ü | Mersey Rivers Trust | Knowsley Council United Utilities Andrea Robson, Environment Agency | £67.500 Landfill tax fund | Veolia | 2021-03-31 | July 2020: Delivery planned for 2020-21 | Developing
Coronation Park (Greasby, Wirral) NFM Project | Surface water flood risk to 8 properties and poor drainage at park limiting use during wet weather |  |  |  | ü | ü | Wirral Council | Paul Corner, Mersey Rivers Trust | ~£150k | FDGiA | 2020 | Feb 2019: Project is being delivered and led by Wirral Council as it is a Council owned park. Paul Corner feeding into project in terms of technical support and helping to achieve multi-benefits. | Developing
Motorway Run-off Surveying water quality & quantity of all river and stream crossing points along the motorway network in Alt/Crossens, Lower Mersey & Douglas Catchments. | Water quality, flood risk, habitat | ü | ü | ü |  |  | Paul Corner, Mersey Rivers Trust Sara Clowes, Groundwork | Highways England LAs Andrea Robson & Helen Dix, Environment Agency Mike Norbury, Mersey Forest | Feasability £200,000 Delivery £2.5m | Highways England Environmental designated Fund |  |  | Developing
Carbon Landscape - Hey Brook Revival Creation of SuDS within Low Hall LNR, volunteer tasks | Water quality, flood risk, habitat | ü | ü | ü |  | ü | Rebecca Howard, Mersey Rivers Trust | EA, Lancs WT, Wigan Council | 36000 | Heritage Lottery | 2021-03-31 | March 2020: River Guardians trained and monitoring ongoing, waer vole survey, leaky dams created, digging works postponed due to poor weather conditions. Digging will resume in Autumn 2020 | In progress
Speke Garston Coastal Reserve - Shoreline | Habitat improvement |  | ü |  | ü |  | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust | Liverpool Sailing Club | 35000 | Any |  |  | Developing
Spike Island | Habitat improvements |  | ü |  | ü |  | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 20000 | Any |  |  | Developing
Ditton Brook | Walkover Surveys | ü | ü |  |  |  | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 10000 | Any |  |  | Developing
Speke Garston Coastal Reserve - Engagement | Engaging the local community in clean-ups etc |  | ü |  |  | ü | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 10000 | Any |  |  | Developing
Ditton Brook Tidal | Biodiversity and litter |  | ü |  |  | ü | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 20000 | Any |  |  | Developing
River Guardians - Court Hey Park and Netherly Brook | Monitoring water quality | ü | ü |  | ü | ü | Mersey Rivers Trust |  | 6000 | WEIF |  | 2019: Submitted to MTP. July 2020: Project not successful for WEIF | Developing

## Completed Projects
Lower Mersey Action Plan
Project Name & Brief Description | Key Drivers | 1. Developing an evidence base | 2. Delivering cleaner and healthier waterbodies | 3. Delivering Integrated Water Management | 4. Opportunities for using the water environment | 5. Engaging the community | Lead (name & org.) | Additional partners (name and org.) | Cost (£) | Target funding streams | Delivery date | Updates | RAG
Borsdane Wood Leaky Dams | Flood risk |  | ü | ü |  | ü | Rebecca Howard, Mersey Rivers Trust | Wigan Council | 2000 | Wigan Council | 2020-03-31 | March 2020: Project complete. 30 leaky dams installed over 3 volunteer days | Completed
M53 SuDS Intercept Motorway run-off through an area of wet-woodland to filter the pollutants. Creation of a BAP priority habitat in a LNR | Water quality, flood risk, habitat | ü | ü | ü |  |  | Paul Corner, Mersey Rivers Trust | Highways England Cheshire West and Chester Council Andrea Robson, Environment Agency Mike Norbury, Mersey Forest | Feasability £20,000 Delivery £100,000 | Highways England Environmental designated Fund |  | Feb 2019: Received £20k for feasability study March 2020: Feasibility study completed. | Completed