## Live Projects
Lower Mersey Action Plan
Project Name & Brief Description | Key Drivers | 1. Developing an evidence base | 2. Delivering cleaner and healthier waterbodies | 3. Delivering Integrated Water Management | 4. Opportunities for using the water environment | 5. Engaging the community | Lead (name & org.) | Additional partners (name and org.) | Cost (£) | Target funding streams | Delivery date | Updates | RAG
Coronation Park (Greasby, Wirral) NFM Project | Surface water flood risk to 8 properties and poor drainage at park limiting use during wet weather |  |  |  | ü | ü | Wirral Council | Mersey Rivers Trust | ~£150k | FDGiA |  | Project is being delivered and led by Wirral Council as it is a Council owned park. Mersey Rivers Trust is feeding into project in terms of technical support and helping to achieve multi-benefits. | Developing
Speke Garston Coastal Reserve - Shoreline | Habitat improvement |  | ü |  | ü |  | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust | Liverpool Sailing Club | 35000 | Any |  |  | Delivery in progress
Spike Island | Habitat improvements |  | ü |  | ü |  | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 20000 | Any |  |  | Delivery in progress
Ditton Brook | Walkover Surveys | ü | ü |  |  |  | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 10000 | Any |  |  | Delivery in progress
Speke Garston Coastal Reserve - Engagement | Engaging the local community in clean-ups etc |  | ü |  |  | ü | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 10000 | Any |  |  | Delivery in progress
Ditton Brook Tidal | Biodiversity and litter |  | ü |  |  | ü | Mersey Rivers Trust, Groundwork, Mersey Gateway Environmental Trust |  | 20000 | Any |  |  | Delivery in progress
River Guardians - Court Hey Park and Netherly Brook | Monitoring water quality | ü | ü |  | ü | ü | Mersey Rivers Trust |  | 4000 | Co-op |  | Training River Guardians | In progress
Sankey Catchment Plan | Habitat improvement, Engagement, Surveys | ü | ü | ü | ü | ü | Groundwork CLM | Catchment Partners, Other partners | >£100k | Any |  | Partners developing HLF bid | Developing
Whittle Brook Water Quality Improvement project | Water quality, NFM, Surveys, Habitat improvement | ü | ü | ü |  |  | Mersey Rivers Trust |  | £147k | Environment Agency WEIF |  | Submitted to the EA Medium Term Plan for a multi-year project | Developing
River Guardians - Wirral | Monitoring water quality | ü | ü |  | ü | ü | Mersey Rivers Trust |  | 5000 | Any |  | Citizen Scientist trained and operating | In progress
Revive Rivacre | Feasibility and design | ü | ü | ü |  |  | Mersey Rivers Trust |  |  | Environment Agency WEIF | 2022-03-31 | Designs produced | In progress
Rivacre RiverCare | Habitat improvements |  | ü |  | ü | ü | Mersey Rivers Trust, Cheshire West and Chester Council | Volunteers | 20000 | People Trust | 2022-03-31 | A community bird hide is being installed | In progress

## Completed Projects
Lower Mersey Action Plan
Project Name & Brief Description | Key Drivers | 1. Developing an evidence base | 2. Delivering cleaner and healthier waterbodies | 3. Delivering Integrated Water Management | 4. Opportunities for using the water environment | 5. Engaging the community | Lead (name & org.) | Additional partners (name and org.) | Cost (£) | Target funding streams | Delivery date | Updates | RAG
Borsdane Wood Leaky Dams | Flood risk |  | ü | ü |  | ü | Rebecca Howard, Mersey Rivers Trust | Wigan Council | 2000 | Wigan Council | 2020-03-31 | March 2020: Project complete. 30 leaky dams installed over 3 volunteer days | Completed
M53 SuDS Intercept Motorway run-off through an area of wet-woodland to filter the pollutants. Creation of a BAP priority habitat in a LNR | Water quality, flood risk, habitat | ü | ü | ü |  |  | Paul Corner, Mersey Rivers Trust | Highways England Cheshire West and Chester Council Andrea Robson, Environment Agency Mike Norbury, Mersey Forest | Feasability £20,000 Delivery £100,000 | Highways England Environmental designated Fund |  | Feb 2019: Received £20k for feasability study March 2020: Feasibility study completed. | Completed
Court Hey Park NFM/SuDS Pilot project highlghted through the NFM opportunity modelling. Project to provide off-line flood storage and at the same time mitigate diffuse pollution in Court Hey Brook. Linked to Court Hey wetland project | Flood risk, water quality, public engagement, volunteering |  | ü | ü | ü | ü | Knowsley Council | Mersey Rivers Trust United Utilities Environment Agency | £10k initial funding. £20k Capital | FDGiA, Local Levy | 2021-03-31 | Delivered in 2020-21 | Delivered
Court Hey Park Wetland Creation Create a wetland in Court Hey Park with improved footpaths for access. | Access and recreation, water quality, public engagement, volunteering |  | ü | ü | ü | ü | Mersey Rivers Trust | Knowsley Council United Utilities Environment Agency | £67,500 Landfill tax fund. | Veolia | 2022-03-31 | Delivery complete | Delivered
Motorway Run-off Proposal for surveying water quality & quantity of all river and stream crossing points along the motorway network in Alt/Crossens, Lower Mersey & Douglas Catchments. | Water quality, flood risk, habitat | ü | ü | ü |  |  | Mersey Rivers Trust Groundwork | Highways England Local Authorities Environment Agency Mersey Forest | Feasability £200,000 Delivery £2.5m | Highways England Environmental designated Fund |  | Funding application not going forward | Not progressing
Carbon Landscape - Hey Brook Revival Creation of SuDS within Low Hall LNR, volunteer tasks | Water quality, flood risk, habitat | ü | ü | ü |  | ü | Mersey Rivers Trust | Environment Agency, Lancashire Wildlife Trust Wigan Council | 36000 | Heritage Lottery | 2021-03-31 | Wetlands created and restored. River Guardians trained, water vole survey, leaky dams created. | Delivered